## Sheet1
Control ID | Risk ID | Risk Description | Annex A Control | Control Description | Control Owner | Applicability | Implementation Status | Evidence | Testing Method | Control Effectiveness | Gap | Remediation | Target Date | Status
ctrl-001 | R-001 | Unauthorized access to customer data through compromised privileged accounts | A.8.5 — Secure authentication | MFA is required for privileged accounts | IAM / Security Team | Yes | Partial | MFA enforcement report | Sample privileged accounts and verify MFA is enabled | Partially Effective | 5% of privileged accounts do not have MFA enabled | Enforce MFA for all remaining privileged accounts | 2026-10-31 | Open
ctrl-002 | R-002 | Malware infection on employee laptops could compromise company information | A.8.7 — Protection against malware | Endpoint protection is deployed and maintained on company laptops | security team | yes | implemented | Endpoint protection deployment report | Review endpoint coverage and sample laptop protection status | Effective | No significant gap identified | None | N/A | Closed
ctrl-003 | R-003 | Former or transferred employees may retain unnecessary access to company systems | A.5.18 — Access rights | User access rights are periodically reviewed and unnecessary access is removed | IT Security Team | yes | partial | access review report | Sample user accounts and compare assigned access with current job responsibilities | Partially Effective | 2 inactive user accounts still have access to a SaaS application | Disable inactive accounts and establish a quarterly access-review process | 2026-10-15 | open